## Tasks
Tasks
Filter by status or owner. Percent complete is a fraction, so 0.5 shows as 50%.
ID | Task | Owner | Status | Priority | Start | Due | Done | Days left
T-01 | Discovery interviews | Sam | Done | High | 2026-01-06 | 2026-01-24 | 1
T-02 | Process map | Sam | Done | High | 2026-01-20 | 2026-02-07 | 1
T-03 | Data model | Rae | In progress | High | 2026-02-03 | 2026-03-07 | 0.6
T-04 | Prototype | Rae | In progress | Medium | 2026-02-17 | 2026-03-21 | 0.35
T-05 | Schema adapter | Kit | Blocked | High | 2026-02-24 | 2026-03-14 | 0.2
T-06 | Parallel run | Team | Not started | High | 2026-03-17 | 2026-04-04 | 0
T-07 | Training material | Jo | Not started | Medium | 2026-03-24 | 2026-04-11 | 0
T-08 | Handover pack | Jo | Not started | Medium | 2026-04-07 | 2026-04-25 | 0
Overall complete

## By owner
By owner
Workload view for the weekly check-in.
Owner | Total tasks | Open | Overdue
Sam
Rae
Kit
Jo

## Milestones
Milestones
The dates the whole team is judged on.
Milestone | Due | Forecast | Status | Owner
Findings report | 2026-02-07 | 2026-02-07 | Met | Sam
Prototype review | 2026-03-21 | 2026-03-21 | On track | Rae
Feature complete | 2026-04-04 | 2026-04-11 | Slipped | Kit
Go live | 2026-05-02 | 2026-05-09 | Slipped | Team